Waabanong Weekly Update

Delivered August 10, 2026

Week of August 3 to 7, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | Complete | Maintenance | Build housekeeping; production environment build underway |
| I2 - Login & Authorization | Complete | Maintenance | No changes this week |
| I3 - Client, Member & Family Data | Complete | Maintenance | No changes this week |
| I4 - Intake Management & Automated Notifications | Complete | Maintenance | No changes this week |
| I5 A - Case File Management & Signs of Safety | Complete | Maintenance | No changes this week |
| I5 B – Abuse Investigations | In Progress | Development | Referral form and offender-handling fixes continue |
| I6 - Data Migration | In Progress | Design | Contingency budget confirmed; production environment build underway |
| I7 - Financial Tracking & Exports for Sage | In Progress | Design | No activity this week |
| I8 - My Dashboard & Reporting | Not Started | — | No activity this week |

- Project Management & General

Weekly Progress

Rob confirmed the FAMCare source data is rougher than anticipated and the project's contingency budget will be drawn on for migration cleanup — exact amount still being assessed

Go-live timeline confirmed slipping again, for two reasons: slower-than-expected live-data access, and staggered UAT pushing back reporting/dashboard module design

Ross reconfirmed his preference to prioritize migration accuracy over the original deadline

Waabanong production environment build kicked off (Aug 4) with IDFusion and PCFS's IT provider, expected to complete within the week

General navigation and log-entry modal usability improvements this week

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

Stopped tracking machine-local dompdf font cache (build cleanup)

Production environment build underway with Campfire/PCFS IT

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

No changes this week.

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

No changes this week.

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

No changes this week.

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

Added gender specification fields to referral forms

Added victim-options retrieval for Report to Abuse forms; related modal functionality updated

Genogram updated to exclude selected victims from offender options, with improved pagination accuracy

Fixed Intake Report Form issue where the offender was not being added to Persons Involved

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

Contingency budget confirmed needed for FAMCare migration cleanup — exact amount still being assessed

Production environment build kicked off (Aug 4), which will allow IDFusion to begin working with a copy of the FAMCare database once complete

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

No activity this week.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

No activity this week.