# Project Status Report — Custom-CMS

Reporting Period: 2026-W31 · 2026-07-17 to 2026-07-23

Marcus Morrisey

2026-07-23

# Project Status Report

| Client | PCFS |
| --- | --- |
| Project | Custom-CMS |
| Docket # | PD25-1186-CO |
| Project Manager | Marcus Morrisey |
| Reporting Date | 2026-07-23 |
| Start Date | 2025-11-17 |
| Planned Finish | 2026-03-31 |
| Estimated Finish | 2026-07-31 |

## Health Dashboard

| Indicator | Status |
| --- | --- |
| Overall Health | 🔴 Red |
| Schedule | 🔴 Red |
| Scope | 🟡 Yellow |
| Budget | 🟡 Yellow |
| Client’s Feeling | 🟢 Green |

## Project Status & Dates

Project Status: The team iterated on the data migration/cutover plan this period — circulated for review July 17, revised per Rob’s feedback July 21–22 — while case file functionality was opened early to unblock UAT scenarios that depend on an existing open case. A new cost signal emerged: Rob flagged that FAMCare’s database structure is unusually poor quality and may require a change request and contingency-budget spend to build reliable migration scripts. Client engagement was notably positive this period — Ross and team were cooperative and accommodating despite a busy Treaty Days week, a welcome contrast to the capacity pushback seen last period.

Variance: Planned finish 2026-03-31 → Estimated finish 2026-07-31 (+122 days)

## Progress This Period

- Data migration/cutover plan (2-page brief) drafted and circulated to Varun, Gabrielle, and Rob for review (July 17); revised per Rob’s feedback and recirculated (July 22).

- Case file functionality opened ahead of schedule so Ross’s team can test intake scenarios that depend on an existing open case.

## Milestones & Schedule

| Milestone | Baseline End | Estimated End | Status | Variance |
| --- | --- | --- | --- | --- |
| M-01: Stage 1 — Discovery and Requirements complete | 2025-12-22 | 2026-03-26 | Delayed | +94d |
| M-02: Stage 2 — Solution Design complete | 2026-01-31 | 2026-03-26 | Delayed | +54d |
| M-03: Stage 3 — All 9 iterations complete / system ready | 2026-03-31 | 2026-07-25 | Delayed | +116d |
| M-04: Go-Live | 2026-03-31 | 2026-07-31 | Delayed | +122d |
| M-05: Stage 4 — Post-launch support complete | 2026-04-30 | 2026-08-28 | Delayed | +120d |

## Decisions Made

| Decision | Made By | Date | Notes |
| --- | --- | --- | --- |
| Access-control testing item dropped from the cutover plan | Marcus / Rob | 2026-07-22 | Rob suggested removing it; Marcus agreed |
| Stress test retained in the cutover plan despite Rob’s suggestion to drop it | Marcus | 2026-07-22 | Ross specifically requested it; Marcus flagged this to Rob rather than unilaterally removing it |
| FamCare will remain accessible (not read-only) for a few months post-cutover, for historical lookups | Rob / Marcus | 2026-07-21 | IDFusion has no access to make FamCare read-only regardless; this will be communicated as an internal message to PCFS staff instead |

## Action Items & Commitments

### New This Period

| # | Owner | Item | Due Date | Status |
| --- | --- | --- | --- | --- |
| A-209 | Varun | Review the revised data migration/cutover plan; confirm test-environment access and whether PHP needs to be installed there for migration scripts | 2026-07-27 | Open |
| A-210 | Marcus | Reconcile signed-SOW status with Rob — a signed copy was already sent to Ross on Jul 15; confirm with Rob/Ross that a copy is on file | 2026-07-23 | Open |
| A-211 | Gabrielle / Ross | Hold the case management module UAT walkthrough (targeting Fri Jul 24 or the following Monday) to formally kick off case file UAT; expand the testing pool with additional service delivery staff | 2026-07-27 | Open |
| A-212 | Gabrielle | Review the finance process for ongoing services with Ross’s team (session planned Jul 23) | 2026-07-23 | Open |
| A-213 | Marcus / Rob | Assess whether a change request and contingency budget are needed to handle FAMCare’s database structure during migration scripting | 2026-07-27 | Open |

### Changed This Period

| # | Owner | Item | Due Date | Status | Update |
| --- | --- | --- | --- | --- | --- |
| A-202 | Marcus | Compile and send Ross a consolidated go-live readiness update covering: training-video documentation scope/approach, go-live order-of-operations/timeline, switch-over/AMS support agreement details, and next-priority roadmap planning (events, Community Circle of Care) | 2026-07-16 | Open | Internally discussed/drafted (Jul 17 recap email) but not yet sent to Ross |
| A-206 | Ross / Varun | Schedule pre-go-live stress test (simultaneous login load test) as part of go-live activities | 2026-07-16 | Open | Reconfirmed as a firm Ross request during cutover-plan review (Jul 21–22); not yet scheduled |

### Carried Forward (No Change)

| # | Owner | Item | Due Date | Status | Periods Open |
| --- | --- | --- | --- | --- | --- |
| ⚠️ A-104 | Christine | Consult Kinship department and QA to ensure licensing and placement info accurately represented in system design | 2026-03-26 | Open | 10 |
| ⚠️ A-118 | Marcus / Gabrielle | Design and implement finance dashboard; GL mapping, PO flow, and summary view confirmed in June 19 session | 2026-04-23 | In Progress | 8 |
| A-127 | Christine / Clemene / Marcus | Provide IDFusion with complete list and definitions of all legal terms used by agency, then cross-reference agency law/regulations with system terminology | 2026-05-07 | In Progress | 7 |
| A-129 | IDFusion / Kelvin | Set up alpha testing access for Kelvin, Christine, and Darryl; formal sign-off procedure still pending | 2026-05-07 | In Progress | 7 |
| A-130 | Marcus | Translate project timeline into Outlook calendar invites for key testing/review milestones | 2026-04-28 | Open | 7 |
| A-131 | IDFusion dev | Implement Apr 13 demo feedback items (footer, gender options, profile types, abuse tab, address history, etc.) | 2026-04-30 | Open | 7 |
| A-135 | IDFusion / Rob / Ross | Define post-go-live support tiers (bronze/silver/gold) and SLAs | 2026-05-28 | Open | 7 |
| A-136 | Bev / Christine / Barry / Clemene | Send all finance templates and forms; RBC bank export column headers still needed | 2026-04-28 | In Progress | 7 |
| A-150 | Marcus / Gabrielle | Update finance PO workflow wireframes and finance tab filter/column changes from Jul 3 review | 2026-05-21 | In Progress | 6 |
| A-151 | Marcus / Gabrielle | Redesign abuse module as intake-form wizard per May 11 reset decision | 2026-05-21 | In Progress | 6 |
| A-152 | Ross / IDFusion | Implement global holiday calendar in Wabanong system settings for SLA calculations | 2026-05-21 | Open | 6 |
| A-153 | Kelvin (PCFS) | Send finalized abuse investigation conclusion terminology; provide provincial abuse form fields for copy-assist mapping | 2026-05-21 | Open | 6 |
| A-155 | Marcus / Darryl Boulanger (PCFS) | Follow up re: missing Manitoba CFS Act abuse issue categories for intake form | 2026-05-21 | In Progress | 6 |
| A-156 | Marcus | Clarify how “parenting time” is determined for case anchoring (both parents Peguis members) | 2026-05-21 | Open | 6 |
| A-157 | Marcus / Gabrielle | Update ongoing services wireframes; schedule follow-up review with CRD team | 2026-05-21 | In Progress | 6 |
| A-160 | Ross (IDFusion) | Document “Finance Assigner” role: queue visibility and task assignment capabilities | 2026-05-21 | Open | 6 |
| A-171 | Marcus (Rob) | Send updated PCFS status report: revised July go-live, abuse as separate iteration, updated meeting cadence | 2026-05-21 | Open | 5 |
| A-176 | Marcus | Clarify which budget pool covers intake-related purchases (operations vs. prevention/family service) | 2026-05-21 | Open | 5 |
| A-177 | Gabrielle | Implement dual supervisor task assignment in intake task modal | 2026-07-02 | Open | 4 |
| A-178 | Gabrielle | Add optional case synopsis/summary field at end of intake form; carry over to case file | 2026-07-02 | Open | 4 |
| A-179 | Gabrielle | Submit development ticket for issue categories expansion to full CFIS list — go-live blocker | 2026-07-02 | Open | 4 |
| A-180 | Ross / Darryl | Schedule follow-up intake practice run sessions; coordinate with Marcus/Gabrielle for follow-up reviews | 2026-07-02 | Open | 4 |
| A-181 | Ross / Gabrielle / Marcus | Define and implement intake supervisor finance permissions | 2026-07-02 | Open | 4 |
| A-182 | Marcus | Activate UAT accounts for newly added team members; send UAT session summary to June 16 participants | 2026-06-18 | Open | 4 |
| A-184 | Gabrielle | Create/confirm bug ticket for “open services” not showing in person search results | 2026-06-18 | Open | 4 |
| A-187 | Rob / Marcus / Gabrielle | Review all shared finance documentation; compile requirements summary and schedule follow-up finance design session | 2026-07-02 | Open | 3 |
| A-189 | Marcus / Ross / Varun | Obtain access to live (scrubbed) FAMCare production data — due date passed 2026-07-15 without resolution | 2026-07-15 | Open | 3 |
| A-197 | Ross / Marcus / Gabrielle | Schedule meeting to align frontline/finance terminology; document funding-determination role ownership | 2026-07-09 | Open | 2 |
| A-201 | IDFusion dev | Implement “Complete Task” button (replacing “Edit Task”) with Yes/No confirmation dialog | 2026-07-09 | Open | 2 |
| A-205 | Ross | Pre-identify key test cases and perform side-by-side checks after DB import | 2026-07-16 | Open | 1 |
| A-208 | Marcus | Check with Gabrielle on current state of service-referral functionality (Rainbow Lodge/Sun Lodge-type referrals) | 2026-07-16 | Open | 1 |

⚠️ = open 8+ periods — flagged for aging review.

## Issues & Risks

### New This Period

None this period.

### Changed This Period

| # | Description | Severity | Owner | Due Date | Update |
| --- | --- | --- | --- | --- | --- |
| I-042 | FAMCare live schema diverges significantly from the test snapshot — risks inaccurate migration scripts if not resolved before finalizing FAMCare→Wabanong migration | Medium-High | Varun / Marcus | 2026-07-09 | Rob flagged (Jul 21) that FAMCare’s current database structure is unusually poor quality, likely requiring a CR and contingency-budget spend to build reliable migration scripts — first concrete cost signal on this risk |
| I-035 | Abuse program — carved out as separate wizard-style iteration | Medium | Marcus / Kelvin / Clemene | 2026-04-30 | Gabrielle confirmed (Jul 22) internal abuse-module testing has just started; UAT not expected to be ready until the week of Aug 3 |

### Carried Forward (No Change)

| # | Description | Severity | Owner | Due Date | Periods Open |
| --- | --- | --- | --- | --- | --- |
| ⚠️ I-018 | Finance/Sage integration requirements incomplete — formal data entry screen design and Sage integration still pending | Medium | Hailey / Marcus | 2026-01-29 | 15 |
| ⚠️ I-029 | Timeline slippage — go-live revised to end of July 2026; formal contract re-baselining still pending | High | Marcus | 2026-02-12 | 13 |
| ⚠️ I-032 | Development timeline at risk — case file, finance, and abuse iterations still ahead | High | Marcus | 2026-03-12 | 11 |
| ⚠️ I-033 | Address-based search confirmed as new development requirement — moved to roadmap | Medium | Marcus | 2026-03-26 | 10 |
| ⚠️ I-034 | Client-side continuity risk — Haley absent 3+ months; Clemene covering; Alice approaching retirement | Medium | Marcus / Ross | 2026-04-07 | 9 |
| I-036 | UAT pipeline fully operational — Freshdesk → ClickUp triage active; client+family data module UAT complete | Low | Gabrielle | 2026-04-30 | 7 |
| I-037 | Demo environment instability — UAT environment set up in PCFS Azure; risk substantially reduced | Medium | Ross / IDFusion | 2026-05-21 | 6 |
| I-038 | Intake form incomplete — full CFIS issue categories expansion confirmed as mandatory pre-go-live requirement | Medium | Marcus | 2026-05-21 | 6 |
| I-039 | Holiday calendar missing — Wabanong timer logic does not yet account for observed holidays | Medium | Ross / IDFusion | 2026-05-21 | 6 |
| I-041 | UAT bug: “open services” not showing in person search results when initiating a new intake | Low | Gabrielle | 2026-06-18 | 4 |
| I-043 | Client requesting event management (Category E) and Community Circle of Care functionality be pulled into near-term planning; no capacity within current schedule | Medium | Marcus | 2026-07-16 | 1 |

⚠️ = open 8+ periods — flagged for aging review.

## Return to Green Plans

### Overall — 🔴 Red (first flagged: 2025-W48)

- Finalize and circulate the data cutover plan once Varun confirms test-environment readiness (A-209)

- Hold the case file UAT walkthrough to unblock that module’s sign-off (A-211)

- Deliver the consolidated go-live readiness update to Ross that’s been pending since last period (A-202)

- Resolve production-data anonymization approach so scrubbed FAMCare data becomes available for migration testing (A-189, I-042)

### Schedule — 🔴 Red (first flagged: 2025-W48)

- Formally re-baseline contract timeline with Clemene/Rob — July 31 go-live target needs a signed-off schedule

- Identify critical path: intake UAT → case file UAT → finance UAT → abuse UAT → go-live; confirm each module’s UAT readiness date

- Schedule pre-go-live stress test as part of go-live activities (A-206)

- Get Varun’s sign-off on the revised cutover plan (A-209)

### Scope — 🟡 Yellow (first flagged: 2025-W50)

- Finance scope now partially locked; complete scope definition after Rob’s documentation review (A-187)

- Hold roadmap/capacity conversation on event management (Category E) and Community Circle of Care to manage scope-expectation risk (I-043)

- Confirm service-referral functionality status with Gabrielle before committing to any scope changes (A-208)

### Budget — 🟡 Yellow (first flagged: 2025-W50)

- Assess FAMCare CR/contingency-budget need before it becomes a blocker on migration scripting (A-213)

- Abuse contract amendment still outstanding (A-171); include in next PCFS status report

## Next Period Plan

- Get Varun’s sign-off on the cutover plan and resolve test-environment/PHP access question (A-209)

- Hold the case management UAT walkthrough and finance-process review for ongoing services (A-211, A-212)

- Send Ross the consolidated go-live readiness update (A-202)

- Confirm signed-SOW status with Rob/Ross (A-210)

- Determine CR/contingency budget need for FAMCare migration work (A-213)