# Project Status Report — Custom-CMS

Reporting Period: 2026-W33 · 2026-07-31 to 2026-08-06

Marcus Morrisey

2026-08-06

# Project Status Report

| Client | PCFS |
| --- | --- |
| Project | Custom-CMS |
| Docket # | PD25-1186-CO |
| Project Manager | Marcus Morrisey |
| Reporting Date | 2026-08-06 |
| Start Date | 2025-11-17 |
| Planned Finish | 2026-03-31 |
| Estimated Finish | 2026-07-31 |

## Health Dashboard

| Indicator | Status |
| --- | --- |
| Overall Health | 🔴 Red |
| Schedule | 🔴 Red |
| Scope | 🟡 Yellow |
| Budget | 🟡 Yellow |
| Client’s Feeling | 🟢 Green |

## Project Status & Dates

Project Status: Rob confirmed to Ross (Jul 30, relayed in an Aug 4 exchange) that the FAMCare source data is rougher than expected, that the project’s contingency budget will need to be drawn on for migration cleanup, and that the go-live timeline is slipping again — citing slower-than-expected live-data access and staggered UAT as the two causes. Ross reconfirmed his preference to prioritize accuracy over the original deadline and is personally driving the production-environment build, which kicked off today with IDFusion and PCFS’s IT provider. Client engagement remains strongly positive despite the schedule news.

Variance: Planned finish 2026-03-31 → Estimated finish 2026-07-31 (+122 days — note: this estimate has now passed without go-live; see Milestones note below)

## Progress This Period

- Ross confirmed he’s meeting with IDFusion and PCFS’s IT provider today (Aug 4) to begin building the Waabanong production environment — expected to complete this week.

## Milestones & Schedule

| Milestone | Baseline End | Estimated End | Status | Variance |
| --- | --- | --- | --- | --- |
| M-01: Stage 1 — Discovery and Requirements complete | 2025-12-22 | 2026-03-26 | Delayed | +94d |
| M-02: Stage 2 — Solution Design complete | 2026-01-31 | 2026-03-26 | Delayed | +54d |
| M-03: Stage 3 — All 9 iterations complete / system ready | 2026-03-31 | 2026-07-25 | Delayed | +116d |
| M-04: Go-Live | 2026-03-31 | 2026-07-31 | Delayed | +122d |
| M-05: Stage 4 — Post-launch support complete | 2026-04-30 | 2026-08-28 | Delayed | +120d |

Note: M-04’s Estimated End (2026-07-31) has now passed without go-live. Evidence this period doesn’t supply a firm replacement date — Rob’s team is to provide a revised timeline once FAMCare database access is obtained and assessed (A-220). Recommend updating this milestone once that arrives.

## Decisions Made

| Decision | Made By | Date | Notes |
| --- | --- | --- | --- |
| Reconfirmed preference to prioritize migration accuracy over the original timeline, even as the timeline slips further | Ross | 2026-08-04 | Direct response to Rob’s question; reaffirms the team’s established risk tolerance |

## Action Items & Commitments

### New This Period

| # | Owner | Item | Due Date | Status |
| --- | --- | --- | --- | --- |
| A-220 | Rob / Varun | Provide an updated contingency-budget usage estimate and revised project timeline once FAMCare database access is obtained and assessed | 2026-08-13 | Open |
| A-221 | Ross | Relay Rob’s UAT-pacing context to PCFS staff and keep expectations aligned as staggered module-by-module testing continues | 2026-08-06 | Open |
| A-222 | Varun | Once the production environment build completes this week, begin working with a copy of the FAMCare database for the data migration | 2026-08-06 | Open |

### Changed This Period

| # | Owner | Item | Due Date | Status | Update |
| --- | --- | --- | --- | --- | --- |
| A-213 | Marcus / Rob | Assess whether a change request and contingency budget are needed for FAMCare’s database structure during migration scripting | 2026-07-27 | Open | Confirmed by Rob (Jul 30) as needed — amount still TBD pending further data assessment |
| A-219 | Marcus / Varun / Ross / Rob | Meet with Campfire Help Desk to begin building the Waabanong production environment | 2026-07-31 | Open | Kickoff meeting confirmed happening today (Aug 4); Ross expects the build completed this week |
| A-202 | Marcus | Compile and send Ross a consolidated go-live readiness update | 2026-07-16 | Open | Still not sent — the newly-confirmed timeline slip (two named causes) makes this increasingly overdue to formalize |

### Carried Forward (No Change)

| # | Owner | Item | Due Date | Status | Periods Open |
| --- | --- | --- | --- | --- | --- |
| ⚠️ A-104 | Christine | Consult Kinship department and QA to ensure licensing and placement info accurately represented in system design | 2026-03-26 | Open | 12 |
| ⚠️ A-118 | Marcus / Gabrielle | Design and implement finance dashboard; GL mapping, PO flow, and summary view confirmed in June 19 session | 2026-04-23 | In Progress | 10 |
| ⚠️ A-127 | Christine / Clemene / Marcus | Provide IDFusion with complete list and definitions of all legal terms used by agency, then cross-reference agency law/regulations with system terminology | 2026-05-07 | In Progress | 9 |
| ⚠️ A-129 | IDFusion / Kelvin | Set up alpha testing access for Kelvin, Christine, and Darryl; formal sign-off procedure still pending | 2026-05-07 | In Progress | 9 |
| ⚠️ A-130 | Marcus | Translate project timeline into Outlook calendar invites for key testing/review milestones | 2026-04-28 | Open | 9 |
| ⚠️ A-131 | IDFusion dev | Implement Apr 13 demo feedback items (footer, gender options, profile types, abuse tab, address history, etc.) | 2026-04-30 | Open | 9 |
| ⚠️ A-135 | IDFusion / Rob / Ross | Define post-go-live support tiers (bronze/silver/gold) and SLAs | 2026-05-28 | Open | 9 |
| ⚠️ A-136 | Bev / Christine / Barry / Clemene | Send all finance templates and forms; RBC bank export column headers still needed | 2026-04-28 | In Progress | 9 |
| A-150 | Marcus / Gabrielle | Update finance PO workflow wireframes and finance tab filter/column changes from Jul 3 review | 2026-05-21 | In Progress | 8 |
| A-151 | Marcus / Gabrielle | Redesign abuse module as intake-form wizard per May 11 reset decision | 2026-05-21 | In Progress | 8 |
| A-152 | Ross / IDFusion | Implement global holiday calendar in Wabanong system settings for SLA calculations | 2026-05-21 | Open | 8 |
| A-153 | Kelvin (PCFS) | Send finalized abuse investigation conclusion terminology; provide provincial abuse form fields for copy-assist mapping | 2026-05-21 | Open | 8 |
| A-155 | Marcus / Darryl Boulanger (PCFS) | Follow up re: missing Manitoba CFS Act abuse issue categories for intake form | 2026-05-21 | In Progress | 8 |
| A-156 | Marcus | Clarify how “parenting time” is determined for case anchoring (both parents Peguis members) | 2026-05-21 | Open | 8 |
| A-157 | Marcus / Gabrielle | Update ongoing services wireframes; schedule follow-up review with CRD team | 2026-05-21 | In Progress | 8 |
| A-160 | Ross (IDFusion) | Document “Finance Assigner” role: queue visibility and task assignment capabilities | 2026-05-21 | Open | 8 |
| A-171 | Marcus (Rob) | Send updated PCFS status report: revised July go-live, abuse as separate iteration, updated meeting cadence | 2026-05-21 | Open | 7 |
| A-176 | Marcus | Clarify which budget pool covers intake-related purchases (operations vs. prevention/family service) | 2026-05-21 | Open | 7 |
| A-177 | Gabrielle | Implement dual supervisor task assignment in intake task modal | 2026-07-02 | Open | 6 |
| A-178 | Gabrielle | Add optional case synopsis/summary field at end of intake form; carry over to case file | 2026-07-02 | Open | 6 |
| A-179 | Gabrielle | Submit development ticket for issue categories expansion to full CFIS list — go-live blocker | 2026-07-02 | Open | 6 |
| A-180 | Ross / Darryl | Schedule follow-up intake practice run sessions; coordinate with Marcus/Gabrielle for follow-up reviews | 2026-07-02 | Open | 6 |
| A-181 | Ross / Gabrielle / Marcus | Define and implement intake supervisor finance permissions | 2026-07-02 | Open | 6 |
| A-182 | Marcus | Activate UAT accounts for newly added team members; send UAT session summary to June 16 participants | 2026-06-18 | Open | 6 |
| A-184 | Gabrielle | Create/confirm bug ticket for “open services” not showing in person search results | 2026-06-18 | Open | 6 |
| A-187 | Rob / Marcus / Gabrielle | Review all shared finance documentation; compile requirements summary and schedule follow-up finance design session | 2026-07-02 | Open | 5 |
| A-189 | Marcus / Ross / Varun | Obtain access to live (scrubbed) FAMCare production data — due date passed 2026-07-15 without resolution | 2026-07-15 | Open | 5 |
| A-197 | Ross / Marcus / Gabrielle | Schedule meeting to align frontline/finance terminology; document funding-determination role ownership | 2026-07-09 | Open | 4 |
| A-201 | IDFusion dev | Implement “Complete Task” button (replacing “Edit Task”) with Yes/No confirmation dialog | 2026-07-09 | Open | 4 |
| A-205 | Ross | Pre-identify key test cases and perform side-by-side checks after DB import | 2026-07-16 | Open | 3 |
| A-206 | Ross / Varun | Schedule pre-go-live stress test — reconfirmed as a firm Ross request (Jul 21–22) | 2026-07-16 | Open | 3 |
| A-208 | Marcus | Check with Gabrielle on current state of service-referral functionality (Rainbow Lodge/Sun Lodge-type referrals) | 2026-07-16 | Open | 3 |
| A-209 | Varun | Review the revised data migration/cutover plan; confirm test-environment access and PHP install needs | 2026-07-27 | Open | 2 |
| A-210 | Marcus | Reconcile signed-SOW status with Rob — confirm with Rob/Ross that a signed copy is on file | 2026-07-23 | Open | 2 |
| A-212 | Gabrielle | Review the finance process for ongoing services with Ross’s team | 2026-07-23 | Open | 2 |
| A-214 | IDFusion dev | Send Rupen and Leanne the test-environment access email and a cheat sheet for logging tickets | 2026-07-30 | Open | 1 |
| A-215 | Ross | Pull the organizational chart from Bamboo and send CRD/supervisor/worker names to IDFusion | 2026-08-06 | Open | 1 |
| A-216 | Ross | Coordinate a pretest session with CRDs and supervisors; send meeting invite (targeting Aug 7) | 2026-08-07 | Open | 1 |
| A-217 | IDFusion dev | Fix two case-file bugs from the Jul 28 UAT walkthrough (case-reference structure, director-reassignment bug) | 2026-08-06 | Open | 1 |
| A-218 | IDFusion dev / Ross | Correct the placement-type dropdown list and create a “Wabanong admin” role before case file UAT resumes | 2026-08-06 | Open | 1 |

⚠️ = open 8+ periods — flagged for aging review.

## Issues & Risks

### New This Period

None this period.

### Changed This Period

| # | Description | Severity | Owner | Due Date | Update |
| --- | --- | --- | --- | --- | --- |
| I-029 | Timeline slippage — go-live revised to end of July 2026; formal contract re-baselining still pending | High | Marcus | 2026-02-12 | Rob explicitly confirmed (Jul 30) the go-live timeline is slipping again, citing two named causes: slower-than-expected live-data access, and staggered UAT delaying reporting/dashboard module design. Formal contract re-baselining still not done. |
| I-042 | FAMCare live schema diverges significantly from the test snapshot; database structure poor quality | Medium-High | Varun / Marcus | 2026-07-09 | Contingency-budget need confirmed as real by Rob — no longer just a possibility; amount still unknown pending further data assessment. |

### Carried Forward (No Change)

| # | Description | Severity | Owner | Due Date | Periods Open |
| --- | --- | --- | --- | --- | --- |
| ⚠️ I-018 | Finance/Sage integration requirements incomplete — formal data entry screen design and Sage integration still pending | Medium | Hailey / Marcus | 2026-01-29 | 17 |
| ⚠️ I-029 | (see Changed This Period above) | High | Marcus | 2026-02-12 | 15 |
| ⚠️ I-032 | Development timeline at risk — case file, finance, and abuse iterations still ahead | High | Marcus | 2026-03-12 | 13 |
| ⚠️ I-033 | Address-based search confirmed as new development requirement — moved to roadmap | Medium | Marcus | 2026-03-26 | 12 |
| ⚠️ I-034 | Client-side continuity risk — Haley absent 3+ months; Clemene covering; Alice approaching retirement | Medium | Marcus / Ross | 2026-04-07 | 11 |
| ⚠️ I-035 | Abuse program — carved out as separate wizard-style iteration; internal testing started; UAT not expected ready until week of Aug 3 | Medium | Marcus / Kelvin / Clemene | 2026-04-30 | 9 |
| ⚠️ I-036 | UAT pipeline fully operational — Freshdesk → ClickUp triage active; client+family data module UAT complete | Low | Gabrielle | 2026-04-30 | 9 |
| I-037 | Demo environment instability — UAT environment set up in PCFS Azure; risk substantially reduced | Medium | Ross / IDFusion | 2026-05-21 | 8 |
| I-038 | Intake form incomplete — full CFIS issue categories expansion confirmed as mandatory pre-go-live requirement | Medium | Marcus | 2026-05-21 | 8 |
| I-039 | Holiday calendar missing — Wabanong timer logic does not yet account for observed holidays | Medium | Ross / IDFusion | 2026-05-21 | 8 |
| I-041 | UAT bug: “open services” not showing in person search results when initiating a new intake | Low | Gabrielle | 2026-06-18 | 6 |
| I-043 | Client requesting event management (Category E) and Community Circle of Care functionality be pulled into near-term planning; no capacity within current schedule | Medium | Marcus | 2026-07-16 | 3 |

⚠️ = open 8+ periods — flagged for aging review.

## Return to Green Plans

### Overall — 🔴 Red (first flagged: 2025-W48)

- Get the updated contingency-budget usage and revised timeline from Rob’s team once DB access is obtained (A-220)

- Begin FAMCare data migration work once the production environment build completes (A-222)

- Deliver the consolidated go-live readiness update to Ross — now more urgent given the confirmed timeline slip (A-202)

- Fix the case-reference and director-reassignment bugs before broader case file testing continues (A-217); correct the placement-type list and stand up the Wabanong admin role (A-218)

- Resolve production-data anonymization approach so scrubbed FAMCare data becomes available for migration testing (A-189, I-042)

### Schedule — 🔴 Red (first flagged: 2025-W48)

- Formally re-baseline contract timeline with Clemene/Rob — go-live target needs a signed-off schedule, now more pressing given the confirmed slip

- Identify critical path: intake UAT → case file UAT → finance UAT → abuse UAT → go-live; confirm each module’s UAT readiness date

- Schedule pre-go-live stress test as part of go-live activities (A-206)

- Hold the CRD/supervisor pretest session targeting Aug 7 (A-216)

### Scope — 🟡 Yellow (first flagged: 2025-W50)

- Finance scope now partially locked; complete scope definition after Rob’s documentation review (A-187)

- Align frontline/finance terminology and funding-determination role ownership (A-197)

- Hold roadmap/capacity conversation on event management (Category E) and Community Circle of Care to manage scope-expectation risk (I-043)

- Confirm service-referral functionality status with Gabrielle before committing to any scope changes (A-208)

### Budget — 🟡 Yellow (first flagged: 2025-W50)

- Get the contingency-budget usage estimate from Rob’s team once DB access is obtained and assessed (A-220)

- Abuse contract amendment still outstanding (A-171); include in next PCFS status report

## Next Period Plan

- Get the contingency-budget usage estimate and revised timeline from Rob’s team (A-220)

- Begin FAMCare data migration once environment build completes (A-222)

- Relay UAT-pacing context to PCFS staff (A-221)

- Send the overdue consolidated go-live readiness update to Ross (A-202)

- Revisit M-04’s Estimated End once the revised timeline arrives