Waabanong Weekly Update

Delivered July 9, 2026

Week of June 29 to July 3, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | In progress | PCFS Testing | Version bumps only |
| I2 - Login & Authorization | In progress | PCFS Testing | No changes this week |
| I3 - Client, Member & Family Data | In progress | PCFS Testing | Person/relationship search fixes; Kinship connection fix |
| I4 - Intake Management & Automated Notifications | In progress | PCFS Testing | Intake reopen workflow added; supervisor review and referral eligibility refinements |
| I5 A - Case File Management & Signs of Safety | In progress | Development | Automated F2F progress; legal status, placement, and case note fixes; No Contact Order badge added |
| I5 B – Abuse Investigations | In Progress | Solution design | No activity this week |
| I6 - Data Migration | In progress | Planning | FAMCare schema export coordination underway; live (scrubbed) data access requested |
| I7 - Financial Tracking & Exports for Sage | In progress | Solution design | No activity this week |
| I8 - My Dashboard & Reporting | Not started |  |  |

- Project Management & General

Weekly Progress

No client meetings this week — a heavy development week with roughly 40 commits across Jun 29–Jul 3, concentrated in Intake Management and Case File / Signs of Safety.

FAMCare data migration coordination continued by email — see I6 for details.

Ross requested a session to review Intake Module workflow changes/additional triggers (following up on a meeting with Darryl); to be scheduled.

Minor housekeeping: search card UI fix and an internal seeder typo correction.

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

No functional infrastructure changes.

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

Complete. No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

Person search: workers are now required to specify relationship type when searching for a person to link (two related fixes).

Fixed: a Kinship connection was not being created correctly.

General relationship-data updates.

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

Intake reopen workflow added — new routes, admin modals, review banners, and task migration to support reopening a closed intake

Supervisor Review improvements: JavaScript cleanup, new "Additional Info" checkbox, simplified task layout, and permissions extended to include the Admin role

Intake reassignment: added the option to reassign an intake to a different worker; fixed a modal overflow issue that was hiding the focus ring

Smaller refinements: multi-add people to an intake from the genogram, prior contact check fixes, updated referral eligibility labels and validation rules, fields remain editable after closure for Admins, "pending closure" added as a search filter, and continued work on issue categories/response-time handling

Ross Gillingham requested a follow-up session to review Intake Module workflow changes and additional triggers, after meeting with Darryl on his first day back (Jun 29); session to be scheduled

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

Continued work on the automated Face-to-Face (F2F) visit workflow.

Legal status module fixes:

  - General bug fixes across the legal status modal

  - Edit mode now correctly pre-selects the existing legal status type

  - Fixed: replacing a document in the legal status modal was not replacing the prior version

  - Legal status and placements now included in the case log

Placements tab: legal status now correctly links to the existing document rather than prompting an upload

Placement improvements:

  - Close date validation added to the new placement modal

  - Additional fields added for placement type

  - Case file placement address fields now match the Person Profile address fields

  - Placement Resource Homes now appear correctly in current households

Case notes:

  - Case note logs now capture when a person is added to or removed from a case

Fixed a special-characters issue in case notes

Genogram: workers can now multi-add people from the genogram directly onto case files

Added a No Contact Order (NCO) badge, shown on genogram and caregiver modals

Log tab: updated visit-log modal; added logging for checklist completion

Added an "All" option to Stage 3 of the Existing Case File modal

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

No new developments this week; solution design continues.

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

FAMCare schema access and export coordination underway with PCFS and their Campfire

Some delays, IDFusion (Varun) granted access to a SQL Dev environment and the FAMCare test database (Jun 29–30)

Initial schema export received (Jun 30) but was not schema-only as expected; Varun identified the correct export method (SQL Server Management Studio → Generate Scripts → script entire database, with Indexes and Foreign Keys enabled, "Schema only" data option) and requested a corrected export

Database structure is complex — roughly 200 tables with inconsistent naming and structure; Ross and Varun began manually mapping tables; PCFS also identified additional data they want carried into the new system that isn't in the current export

PCFS's team is meeting internally this week to confirm exactly what needs to be exported

Access to live (scrubbed) production data has been requested, needed to confirm what data PCFS actually uses before migration scripts are finalized — targeted within two weeks

- I7 - Financial Tracking & Exports for Sage

Features Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

Finance form and PO wireframes were presented to the Finance team.

New draft in progress based on that feedback

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

Future iteration per schedule (no dashboard/reporting work this week).