Waabanong Weekly Update

Delivered June 29, 2026

Week of June 22 to 26, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | In progress | PCFS Testing |  |
| I2 - Login & Authorization | In progress | PCFS Testing |  |
| I3 - Client, Member & Family Data | In progress | PCFS Testing | Genogram improvements: relationship display and case/intake person links |
| I4 - Intake Management & Automated Notifications | In progress | PCFS Testing | Eligibility check moved to Supervisor Review section; intake prior contacts and self-intake fixes |
| I5 A - Case File Management & Signs of Safety | In progress | Development | Placement module improvements; case notes timestamp fix; CFSIS ID fix |
| I5 B – Abuse Investigations | In Progress | Solution design |  |
| I6 - Data Migration | In progress | Planning |  |
| I7 - Financial Tracking & Exports for Sage | In progress | Solution design | Rob reviewing shared documentation; follow-up session to be scheduled |
| I8 - My Dashboard & Reporting | Not started |  |  |

- Project Management & General

Weekly Progress

W27 status report finalized and filed.

Finance module next steps in motion — documentation sharing completed with Rob; review underway ahead of follow-up design session.

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

No infrastructure changes this week.

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

Genogram improvements shipped:

Relationship display updated to correctly include relationship modifiers (e.g., step, adoptive)

Genogram links added for persons involved in cases and intakes — direct navigation from the genogram to related records

Chain link icon display fix

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

Eligibility Check moved to the Supervisor Review section of the intake workflow.

Intake prior contacts and related fixes:

Fixed: prior contacts missing when viewing intake in edit mode

Case file link wired up in the prior contacts section — workers can navigate directly to related case files

Fixed: self-intake fields not being saved correctly

Document replacement logic improved — updating a document now correctly replaces the prior version.

Person activity logging updates.

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

Placement module improvements:

Fixed: resource home type not displaying caregiver information

Placement search fix

Placement end date validation added

Case notes: fixed timestamp reset issue — editing a case note no longer resets the original event date/time.

Fixed: CFSIS ID not updating correctly after admin edits.

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

No new developments this week; solution design continues.

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

No data migration activity this week.

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

Finance module in solution design following June 19 requirements session — Rob reviewing shared documentation (GL codes, funding stream maps, PO forms, policy manual); follow-up design session to be scheduled on completion.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

Future iteration per schedule (no dashboard/reporting work this week).