| Project Status Report | Reporting Date: March 12, 2026 |
| --- | --- |

| Project Details |  |
| --- | --- |
| Client: Peguis Child and Family Services Project Name: Custom CMS Project Docket #: PD25-1186-CO Project Manager/Lead: Marcus Morrisey | Status: In Progress Start Date: Nov 17, 2025 Planned Finish Date: Mar 31, 2026 Estimated Finish Date: TBD – re-baseline pending |

| Status Summary | Health Report |
| --- | --- |
| Project Status: Stage 1 – Discovery & Requirements - Complete — requirements and specifications finalized Stage 2 – High-Level Solution Design - Complete — all major design decisions confirmed; visual designs shared with PCFS team Stage 3 – Iterative Implementation & Deployment — In Progress - Iteration 1 (Login, Search, Person Record): actively in development as of Mar 10; dev team building - Iteration 2 (Intake Workflow): wireframes complete; visual design underway with designers - Iteration 3 (Notifications & Task Assignment): design started Mar 10 with Marcus and Gabrielle - Iterations 4-9: pending re-baseline and velocity measurement from Iteration 1 | Overall Health; Yellow. Schedule; Red. Scope; Yellow. Budget; Yellow. Team's Feeling; Green. Why Yellow or Red Status?. Schedule — Red: Only Iteration 1 of 9 is in development as of Mar 10; the Mar 31 baseline cannot be met. Development started Feb 24 with re-baselining required once Iteration 1 velocity is measured. Scope — Yellow: Address-based search confirmed as a new deliverable (Mar 10). Notification system external integration is being scoped. Budget — Yellow: Sage 300 integration scope not yet confirmed; version/build pending from client contact.. Return to Green Plan. - Re-baseline M-03 and M-04 after Iteration 1 velocity data is available - Assess address-based search impact on iteration sequencing - Finalize notification system design scope before Iteration 2 planning begins - Obtain Sage 300 version/build to define integration scope and cost. |

| Project Milestones |  |  |
| --- | --- | --- |
| Milestone | Status | Estimated End |
| Stage 1 – Discovery & Requirements | Delayed | Mar 26, 2026 |
| Stage 2 – High-Level Solution Design | Delayed | Mar 26, 2026 |
| Stage 3 – Iterative Implementation & Deployment | Delayed | TBD* |
| Stage 4 – Post-Launch Support & Maintenance | On Track | TBD* |
| *Re-baseline required for Stages 3 and 4 once Iteration 1 velocity is measured. |  |  |

| Issues |  |  |
| --- | --- | --- |
| Description | Status | Potential Action Items |
| I-029 – Pilot timeline slippage: original mid-Jan target missed; M-03 baseline days away with only Iter 1 in development | High | Re-baseline after Iteration 1 velocity measured (A-082) |
| I-032 – Development timeline at risk: 9 iterations required; address-based search adds further scope | High | Monitor Iteration 1 progress; accelerate remaining requirements work |
| I-011 – Infrastructure delayed: Azure environment setup pending Campfire resource availability | Medium | Ross to confirm resource timeline; escalate if unresolved by next period |
| I-018 – Finance/Sage integration incomplete: Sage 300 version/build not yet received | Medium | Follow up with Barry/Bev on Sage 300 version (A-079) |
| I-033 – Address-based search adds scope to constrained timeline; iteration impact not yet assessed | Medium | Document as confirmed scope addition; assess iteration sequencing impact |

PCFS Custom CMS: Iteration Progress

Bi-Weekly Status Update — Iteration Progress Table

Reporting Period: Feb 27, 2026 – Mar 12, 2026

Project: PCFS Custom Case Management System

| PCFS Custom CMS – Iteration Progress |  |  |  |
| --- | --- | --- | --- |
| Iteration | Tasks | Progress | Notes |
| 1 – Login, Search & Person Record | - Login screen (M365 SSO) - Search with partial/wildcard matching - Add/Edit person record - Role-based tab access - Sensitive field masking (SIN, health numbers) | In Progress | Dev team (Varun, Omer, awaisamir23) actively building. Started Feb 24. Architecture: Microsoft Entra auth, Laravel + Blade, Spatie RBAC. Visual designs reviewed with Christine, Christina, and Ross on Mar 3. |
| 2 – Intake Workflow | - Intake workflow design - Eligibility screening logic - Combined case management tab - High-risk alerts - Supervisor review | Design Complete | Wireframes finalized and handed to visual designers (Gabrielle) during this period. Visual design in progress as of Mar 10. Development begins after Iteration 1 UAT. |
| 3 – Notifications & Task Assignment | - In-app notification system - Microsoft REST API for external notifications - Task assignment workflow - Supervisor escalation logic | Design In Progress | Design started Mar 10 (Marcus + Gabrielle). External notifications via MS REST API confirmed; no sensitive data in messages. Agency email account for sends TBD (Ross). |
| 4 – Case Management (Signs of Safety) | - Case lifecycle definition - Signs of Safety workflow mapping - Case roles & reassignment logic | Not Started | High-level alignment confirmed. Detailed design deferred until Iterations 1–3 are in development. |
| 5 – Address-Based Search & Search Enhancements | - Address-based search tab - Search over existing address fields - Results filterable by case status - After-hours safety use cases | Not Started | Confirmed as new deliverable Mar 10. Searches existing fields (not creating address objects). After-hours team consultation required (A-107). |
| 6 – Notes, Docs & Supervision | - Case note standards review - Document management concepts - Supervisory review requirements | Not Started | Requirements captured from policy review. Will rely on Iteration 4 case structures. |
| 7 – Data Migration | - Migration strategy planning - Deduplication approach - Validation rules - Source data assessment | Not Started | External consultant involvement to be confirmed. Migration complexity dependent on legacy Fam Care data structure. |
| 8 – Finance & Integration | - Sage 300 requirements - Finance codes & identifiers - Integration approach | Initial Discovery Complete | Finance requirements workshop completed. Sage 300 version/build pending from client (I-018). Integration expected to be output-based (exports/API-ready). |
| 9 – Dashboard & Reporting | - Role-based dashboard concepts - Task and alert aggregation - Reporting foundations | Not Started | "My Dashboard" concept proposed. Design deferred until earlier workflow iterations are finalized. |