# Project Status Report — Custom-CMS

Reporting Period: 2026-W13 · 2026-03-13 to 2026-03-26

Marcus Morrisey

2026-03-26

# Project Status Report

| Client | PCFS |
| --- | --- |
| Project | Custom-CMS |
| Docket # | PD25-1186-CO |
| Project Manager | Marcus Morrisey |
| Reporting Date | 2026-03-26 |
| Start Date | 2025-11-17 |
| Planned Finish | 2026-03-31 |
| Estimated Finish | 2026-06-30 |

## Health Dashboard

| Indicator | Status |
| --- | --- |
| Overall Health | 🔴 Red |
| Schedule | 🔴 Red |
| Scope | 🟡 Yellow |
| Budget | 🟡 Yellow |
| Client’s Feeling | 🟡 Yellow |

## Project Status & Dates

Project Status: Development is actively underway in an iterative delivery model; however, the project is significantly behind the original March 31 baseline, with a revised completion estimate of June 2026 confirmed this period. Key client-side leadership has transitioned — Ross Gillingham has assumed the CIO role for PCFS and Clemene is covering Haley’s responsibilities during a 3-month absence — and finance stakeholder engagement has been confirmed to begin at the April 7th in-person meeting.

Variance: Planned finish 2026-03-31 → Estimated finish 2026-06-30 (+91 days)

## Progress This Period

- Held project onboarding session with Ross Gillingham (new PCFS CIO) and Clemene (covering Haley during 3-month absence)

- Provided full development status update: iterative approach, current modules (person, intake, case management), and timeline revised to June 2026

- Established new biweekly in-person meeting cadence at ID Fusion starting April 7th

- Agreed on UAT approach: anonymized real-world scenarios with staff feedback loops

- Agreed to maintain a product roadmap / parking lot for out-of-scope feature requests

## Milestones & Schedule

| Milestone | Baseline End | Estimated End | Status | Variance |
| --- | --- | --- | --- | --- |
| M-01 — Stage 1: Discovery & Requirements complete | 2025-12-22 | 2026-03-26 | Delayed | +94d |
| M-02 — Stage 2: Solution Design complete | 2026-01-31 | 2026-03-26 | Delayed | +54d |
| M-03 — Stage 3: All 9 iterations complete / system ready | 2026-03-31 | 2026-06-30 | Delayed | +91d |
| M-04 — Go-Live | 2026-03-31 | 2026-06-30 | Delayed | +91d |
| M-05 — Stage 4: Post-launch support complete | 2026-04-30 | 2026-04-30 | On Track | On time |

## Decisions Made

| Decision | Made By | Date | Notes |
| --- | --- | --- | --- |
| Ross Gillingham confirmed as PCFS CIO — primary coordination/approval contact, replacing Haley | Ross, Clemene, Rob, Marcus | 2026-03-23 | AJ and Campfire continue managing technical work/scheduling |
| Clemene covering Haley’s role during 3-month absence (possibly longer) | Clemene | 2026-03-23 | Clemene requires full project orientation |
| Project timeline revised to June 2026; no additional cost to agency | Rob | 2026-03-23 | Only out-of-scope additions would trigger extra cost |
| Biweekly in-person meetings at ID Fusion, starting April 7th at 1:00 PM | All | 2026-03-23 | Christine to send recurring invite; Ross/Marcus to hold additional weekly check-ins as needed |
| UAT approach: sanitized/anonymized real-world scenarios | Rob, Ross, Marcus | 2026-03-23 | Staff test edge cases and provide feedback before moving to next module |
| Finance integration discussions to begin early, before module reaches development | All | 2026-03-23 | CFO, Director of Finance, Senior Finance Officer to be included from April 7th |
| Product roadmap / parking lot to be maintained for out-of-scope feature requests | Rob, Ross | 2026-03-23 | Out-of-scope items communicated clearly and documented for future phases |

## Action Items & Commitments

| # | Owner | Item | Due Date | Status | Carried Over? |
| --- | --- | --- | --- | --- | --- |
| A-036 | Ross Gillingham | Stand up test environment with IP whitelisting for IDFusion access | 2026-01-31 | Open | Yes |
| A-055 | Hailey / Marcus | Clarify and document requirements for role-based access, high-profile cases, and conflict-of-interest restrictions | 2026-01-29 | Open | Yes |
| A-078 | Marcus | Prepare field-definitions Excel template (tab per screen, field names, dropdown values, rules column) | 2026-01-29 | Open | Yes |
| A-079 | Barry / Bev | Provide exact Sage 300 version/build number for integration documentation | 2026-01-29 | Open | Yes |
| A-082 | Marcus | Establish revised target dates; prepare status update for Jaren and Rob with technical challenges and revised timeline | 2026-02-12 | Open | Yes |
| A-083 | Marcus / Varun | Complete Iteration 1 development | 2026-02-12 | Open | Yes |
| A-097 | Marcus / Ken | Arrange Azure environment walkthrough/orientation session for dev team | 2026-03-12 | Open | Yes |
| A-104 | Christine | Consult Kinship department and QA to ensure licensing and placement info accurately represented in system design | 2026-03-26 | Open | Yes |
| A-105 | Marcus / Ross | Determine agency email account for external notification sends (Microsoft REST API integration) | 2026-03-26 | Open | Yes |
| A-106 | Marcus | Implement address-based search tab (search address fields on existing records; show associated individuals/cases, prioritized by open status) | 2026-03-26 | Open | Yes |
| A-107 | Marcus | Consult after-hours team to capture any additional requirements for address-based search feature | 2026-03-26 | Open | Yes |
| A-108 | Clemene | Bring CFO (Bev Stranger), Director of Finance (Barry Mann), and Senior Finance Officer (Carrie) to April 7th in-person meeting | 2026-04-07 | Open | No |
| A-109 | Clemene | Provide Marcus with finance contact email for follow-up and summary sharing from last finance meeting | 2026-04-07 | Open | No |
| A-110 | Christine | Send recurring calendar invite for biweekly in-person meetings starting April 7th (all relevant participants) | 2026-04-07 | Open | No |
| A-111 | Rob | Prepare and circulate agenda for April 7th meeting | 2026-04-04 | Open | No |
| A-112 | Clemene / Rob | Review contract and create a revised, clean project timeline and implementation schedule | 2026-04-07 | Open | No |
| A-113 | Ross / Marcus | Schedule internal debrief prior to April 7th meeting | 2026-04-04 | Open | No |

## Issues & Risks

| # | Description | Severity | Owner | Due Date | Status |
| --- | --- | --- | --- | --- | --- |
| I-011 | Campfire infrastructure delayed — UAT environment setup was pending resource availability from other Campfire client projects | Medium | Marcus / Ross | 2026-01-31 | Closed 2026-03-31 |
| I-018 | Finance/Sage integration requirements incomplete — Sage version/build not received; CFO and Director of Finance not yet engaged in requirements sessions | Medium | Hailey / Marcus | 2026-01-29 | Open |
| I-029 | Timeline slippage — original delivery targets missed; revised completion estimate is June 2026; M-03 baseline (2026-03-31) now missed with Iteration 1 still in progress; re-baselining in progress (A-112) | High | Marcus | 2026-02-12 | Open |
| I-032 | Development timeline at risk — 9 iterations required; address-based search adds scope; revised June estimate communicated to client; re-baselining underway | High | Marcus | 2026-03-12 | Open |
| I-033 | Address-based search confirmed as new development requirement — adds scope to constrained timeline; impact on iteration sequencing not yet assessed | Medium | Marcus | 2026-03-26 | Open |
| I-034 | Client-side continuity risk — Haley absent for 3+ months; Clemene covering but requires full project orientation; risk of decision delays and requirements gaps during transition | Medium | Marcus / Ross | 2026-04-07 | Open |

## Return to Green Plans

### Overall — Red (first flagged: 2025-W48)

- Complete revised project timeline with June target (A-112, Clemene + Rob) and share with all stakeholders

- Engage finance decision-makers (CFO, Director of Finance) starting April 7th to close remaining requirements gap

- Maintain biweekly in-person cadence with clear agendas to improve oversight and accountability

### Schedule — Red (first flagged: 2025-W48)

- Produce revised, signed-off project timeline via A-112; update M-03/M-04 estimated ends once confirmed

- Measure iteration velocity after Iteration 1 completes; use as basis for realistic remaining schedule

- Prioritize unblocking open action items (A-078, A-082, A-097) that affect iteration sequencing

### Scope — Yellow (first flagged: 2025-W50)

- Document address-based search as confirmed scope addition; assess timeline and iteration sequencing impact (I-033, A-106)

- Finalize notification system design scope before Iteration 2 planning begins

- Monitor for additional requirements emerging from finance stakeholder engagement starting April 7th

### Budget — Yellow (first flagged: 2025-W50)

- Obtain Sage 300 version/build number to define integration scope and cost impact (A-079); Bev Stranger (CFO) now confirmed for April 7th meeting — resolution path exists

### Client’s Feeling — Yellow (first flagged: 2026-W13)

- Bring Clemene fully up to speed via Ross/Marcus internal debrief (A-113) and April 7th in-person meeting

- Address Clemene’s training/documentation concern by confirming a documentation plan before go-live

- Maintain product roadmap visibility so client understands scope and future feature pathway

## Next Period Plan

- Hold April 7th in-person meeting: development status demo (intake module), finance stakeholder engagement, revised timeline review

- Ross/Marcus internal debrief to align on project details and communication protocols (A-113)

- Christine sends recurring biweekly meeting calendar invite (A-110)

- Rob circulates April 7th meeting agenda (A-111)

- Clemene/Rob begin revised project timeline and implementation schedule (A-112)

- Continue Iteration development; target Iteration 1 completion for velocity measurement