Waabanong Weekly Update

Delivered July 27, 2026

Week of July 20 to 24, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | Complete | Maintenance | Version bump alongside abuse-module feature flag rollout |
| I2 - Login & Authorization | Complete | Maintenance | No changes this week |
| I3 - Client, Member & Family Data | Complete | Maintenance | No changes this week |
| I4 - Intake Management & Automated Notifications | Complete | Maintenance | No changes this week |
| I5 A - Case File Management & Signs of Safety | In Progress | Bug Fix | Legal Status and Resource Home review task bugs fixed |
| I5 B – Abuse Investigations | In Progress | Development | Heavy referral-form and investigation-record development |
| I6 - Data Migration | In Progress | Design | Cutover plan under review; contingency-budget risk first flagged (no dev commits this week) |
| I7 - Financial Tracking & Exports for Sage | In Progress | Design | No activity this week |
| I8 - My Dashboard & Reporting | Not Started | — | No activity this week |

- Project Management & General

Weekly Progress

Rob reviewed the data migration/cutover plan (Jul 21) and flagged that FAMCare's database structure is rougher than anticipated — the migration will likely require the project's contingency budget; kept the pre-go-live stress test in the plan at Ross's specific request

Confirmed FamCare will remain accessible (not read-only) for a few months post-cutover so staff can look up historical records; this will be communicated internally rather than enforced in the app, since IDFusion has no access to modify FamCare

Case management module UAT walkthrough scheduled via email — targeting Friday Jul 24 or the following Monday — to formally kick off case file UAT and bring two new CRD testers into the pool

Ross confirmed (Jul 24) readiness to begin building the Waabanong production environment, with a kickoff meeting planned with Campfire Help Desk for the following week

Abuse Module UAT confirmed not expected ready until the week of Aug 3, as internal testing on the module was just getting underway

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

Version bump alongside this week's abuse-module feature flag work

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

No changes this week.

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

No changes this week.

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

Fixed Legal Status Expiry Check autogenerated tasks not appearing

Fixed 90-Day Resource Home review task not appearing

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

Referral forms enhanced with required field validations, custom date-range filters, and improved pagination

Investigation activity and referral form improvements for data integrity

Abuse module authorization improvements, PDF snapshot handling, and address management in referral forms

Offender role handling improved in investigation records and search queries for accuracy

Feature flag added for the abuse module ahead of internal testing rollout

General abuse module bug fixes

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

Cutover plan (drafted the prior week) reviewed and revised based on IDFusion's own internal feedback

FAMCare's database structure identified as rougher than expected, which will likely require use of the project's contingency budget for migration cleanup

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

No activity this week.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

No activity this week.