Waabanong Weekly Update

Delivered August 3, 2026

Week of July 27 to 31, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | Complete | Maintenance | Version bump |
| I2 - Login & Authorization | Complete | Maintenance | No changes this week |
| I3 - Client, Member & Family Data | Complete | Maintenance | Genogram search pagination added |
| I4 - Intake Management & Automated Notifications | Complete | Maintenance | No changes this week |
| I5 A - Case File Management & Signs of Safety | In Progress | Bug Fix | Case file UAT walkthrough held; two bugs found and fixed |
| I5 B – Abuse Investigations | In Progress | Development | Victim/offender selection logic and reporting refined |
| I6 - Data Migration | In Progress | Design | Contingency-budget need confirmed; timeline reassessment underway (no dev commits this week) |
| I7 - Financial Tracking & Exports for Sage | In Progress | Design | No activity this week |
| I8 - My Dashboard & Reporting | Not Started | — | No activity this week |

- Project Management & General

Weekly Progress

Case file/ongoing-services UAT walkthrough held (Jul 28) with two new CRD testers (Rupen, Leanne) — full walkthrough of case creation, case notes, placements, legal status, signs of safety, face-to-face visits/AMR plans, documents, and the finance-tab stub

Two bugs surfaced during the walkthrough and immediately queued for fixes:

Child-in-care cases were opening under the parent instead of the child — needs a case-creation dropdown to select the child

Reassigning a case's supervisor was incorrectly also changing the assigned director

Follow-up items from the walkthrough: send test-environment access and a ticket-logging cheat sheet to the new testers; pull the PCFS organizational chart from Bamboo for test-user setup; coordinate a pretest session with CRDs and supervisors targeting Aug 7

Rob flagged (Jul 30) that the FAMCare source data is rougher than anticipated, confirming the project's contingency budget will be drawn on for migration cleanup — exact amount still being assessed

Go-live timeline confirmed slipping again, per Rob, for two reasons: slower-than-expected live-data access, and staggered UAT pushing back reporting/dashboard module design

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

Version bump

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

Pagination added to genogram search results

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

No changes this week.

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

Fixed Case File Placement Types not matching spec — corrected the placement-type dropdown list, addressing the bug found during the Jul 28 UAT walkthrough

Clarified reassignment logic in CaseFileController for worker, supervisor, and director roles — addresses the director-reassignment bug found during the walkthrough

Case file tab handling updated to use query parameters instead of hash fragments for more reliable URL/tab management

Mandatory checklist modal actions streamlined: added "Close without Saving" and "Save & Close" buttons

Fixed button title encoding issue in the supervisor review modal

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

Consultation request linking added to review tasks; task-creation logic enhanced

Active investigation logic improved for clearer, more accurate badge display

Log entry display enhanced to prioritize the full message over the action badge for abuse reports

Fixed sync logic to preserve alleged offenders during intake saves

Improved victim/offender selection logic in the report-to-abuse modal — prevents a selected victim from also appearing as an offender option

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

Rob confirmed the contingency budget will be needed for FAMCare migration cleanup, though the exact amount is still being assessed

Timeline reassessment underway — go-live is slipping again due to slower-than-expected live-data access and staggered UAT pushing back other module work

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

No activity this week.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

No activity this week.