Waabanong Weekly Update

Delivered July 20, 2026

Week of July 13 to 17, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | In progress | PCFS Testing | No changes this week |
| I2 - Login & Authorization | In progress | PCFS Testing | No changes this week |
| I3 - Client, Member & Family Data | In progress | PCFS Testing | No changes this week |
| I4 - Intake Management & Automated Notifications | In progress | PCFS Testing | Development and bug fixes continue |
| I5 A - Case File Management & Signs of Safety | In progress | Development | No activity this week |
| I5 B – Abuse Investigations | In Progress | Solution design | No activity this week |
| I6 - Data Migration | In progress | Planning | Anonymization approach for production-data snapshot still being evaluated |
| I7 - Financial Tracking & Exports for Sage | In progress | Solution design | No new activity this week |
| I8 - My Dashboard & Reporting | Not started |  |  |

- Project Management & General

Weekly Progress

End-of-project planning session (Jul 13) covered three go-live readiness threads: screen-by-screen training-video documentation, production-database anonymization for migration testing, and the go-live order-of-operations/timeline — see I6 for the migration piece. IDFusion will follow up with Rob on training-video scope and send Ross a detailed go-live sequencing plan.

A pre-go-live stress test (simultaneous-login load test) will be scheduled as part of go-live activities.

Ross raised interest in bringing event management and Community Circle of Care functionality into near-term planning; IDFusion confirmed the team does not have capacity for this within the current schedule and will follow up with a roadmap conversation once PCFS gathers detailed requirements internally.

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

No infrastructure changes this week.

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

No authentication changes this week.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

No changes this week.

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

Development and bug fixes continue for Intake Management.

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

No new developments this week.

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

No new developments this week; solution design continues.

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

Production-data anonymization approach still being scoped — IDFusion (Varun) is evaluating a data-obfuscation tool (Data Veil) and consulting on alternative approaches, alongside finalizing exactly which data fields need to migrate from FAMCare.

PCFS agreed to pre-identify key test cases so that, once the database import is complete, both teams can perform side-by-side checks confirming all required data imported correctly and no sensitive information remains exposed.

Target timeline for obtaining a scrubbed production-data snapshot has passed without resolution; this remains the primary blocker for migration testing and is being actively worked.

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

No new activity this week; finance module remains in solution design.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

Future iteration per schedule (no dashboard/reporting work this week).