Waabanong Weekly Update

Delivered May 27, 2026

Week of May 18 to 22, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | In progress | Setting up Testing | Azure Testing environment data migration in progress |
| I2 - Login & Authorization | In progress | PCFS Testing |  |
| I3 - Client, Member & Family Data | In progress | PCFS Testing | Enhancements and fixes this week: person profile updates, improved person search (multi-word + typo tolerance), and profile-type conversion/synchronization fixes. |
| I4 - Intake Management & Automated Notifications | In progress | IDF Testing | Multiple bug fixes validated through internal testing. |
| I5 A - Case File Management & Signs of Safety | In progress | Solution design | Solution design specifications for Case Overview, Case Notes, Placements & SOS are in progress. |
| I5 B – Abuse Investigations | In Progress | Solution design | PCFS workflows integrated. Version two wireframes in progress |
| I6 - Data Migration | In progress | Planning | Working with Campfire to determine how to access data and maintain privacy/security |
| I7 - Financial Tracking & Exports for Sage | In progress | Solution design | Advanced wireframes for PO and credit-card reconciliation in progress; next finance working session pending |
| I8 - My Dashboard & Reporting | Not started |  |  |

- Project Management & General

Weekly Progress

Continued coordination with PCFS and internal alignment on upcoming priorities (person profile + intake stability, then case wireframes/design).

Prepared a plain-language MVP summary for client review covering Login, Person creation, Genogram, and Address Book expectations.

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

Azure testing environment deployed for UAT.

No client-facing changes this week; internal validation continues as the environment is stabilized.

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

User testing launched Wed May 20th.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

Implemented and validated multiple person-profile improvements: profile updates, profile-type conversion handling, and cross-tab synchronization so updates reflect consistently.

Improved person search to better support multi-word queries and tolerate minor typos; refined related task/profile display behaviors.

User testing launched Wed May 20th, and ends June 3rd

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

Significant intake refinements this week: eligibility logic improvements, intake log sorting/notes display, household snapshot display fixes, and multiple bug fixes (including manual entry saving and “Date & Time Received” stability).

Permissions and roles refinements for intake routing and task assignments

- I5 A - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

No new client workshop sessions this week; solution design work continues based on prior Service Delivery walkthroughs.

Automated tasks triggered during case file has been defined and incorporated into the solution

Wireframes and solution design are progressing; next review session to be scheduled as needed with PCFS.

- I5 B – Abuse Investigations

Features Triggers and integration with Intake module Investigation workflow Investigation document management

Weekly Progress

No additional external review this week; Abuse Investigations remains in solution design, incorporating PCFS workflows.

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

Data migration planning continues with Campfire, focusing on secure access, privacy, and approach for trial migrations.

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

Finance work remains queued for the next working session; no new finance work this week.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

Future iteration per schedule (no dashboard/reporting work this week).