Waabanong Weekly Update

Week of April 28, 2026

| Iteration | Status | Current phase | Notes |
| --- | --- | --- | --- |
| I1 - System Infrastructure & Environments | In progress | Setting up Testing | Azure Testing environment data migration in progress |
| I2 - Login & Authorization | In progress | IDF Testing | Session timeout and logout management improvements deployed |
| I3 - Client, Member & Family Data | In progress | IDF Testing | Profile age checks and profile conversion logic merged; bug-fix cycles ongoing |
| I4 - Intake Management & Automated Notifications | In progress | In development | Major iteration shipped (PRs #26–#28); intake-to-case workflow refined per Ongoing Service walkthrough |
| I5 - Case File Management & Signs of Safety | In progress | Solution design | First wireframe walkthrough with PCFS Ongoing Service Team completed Apr 29; design updates queued |
| I6 - Data Migration | In progress | Planning | Working with Campfire to determine how to access data and maintain privacy/security |
| I7 - Financial Tracking & Exports for Sage | In progress | Discovery → Solution design | Finance design session Apr 28; advanced wireframes for PO and credit-card reconciliation in progress |
| I8 - My Dashboard & Reporting | Not started |  |  |

- Project Management & General

Weekly Progress

Abuse Investigation module — two deep design sessions completed Apr 28; module workflow defined including intake handling, investigation lifecycle, evidence references, freeze on reporting, three-tier access management (regular / confidential / restricted), and request-closure workflow with auto-fill final report.

Finance module working session Apr 28 — covered PO and credit-card reconciliation, role-based task assignment (finance assigner role), RBC export/import, audit/compliance, and global holiday calendar; recurring Tuesday finance working sessions confirmed.

Ongoing Service Team — first wireframe walkthrough completed Apr 29 (two parts).

  - Covered intake-to-case handoff (cases first assigned to reconciliation directors, who then choose supervisor and worker), household / genogram, persons-in-case with address and in-home / out-of-home status, related cases, notifications vs. case history logging.

  - Confidentiality and safety — agreed to manage conflict-of-interest under safety/confidentiality using an inclusion-based access model (only assigned worker, supervisor, director).

  - Case attachments and mandatory checklists discussed (rename to “mandatory Child Services checklist”); financial face sheet implications for ending paid care and extended-family visits flagged for follow-up.

Active development continued — session timeout/logout management, eligibility banner messaging, sticky intake header, Safari date picker fix, profile age checks and profile conversion logic; PRs #26 (intake-edit), #27 and #28 (bug-fix batches) merged to master.

- I1 - System Infrastructure & Environments

Features Set up Development, Testing, and Production environments

Weekly Progress

No new updates this period — Azure environment data migration continues in the background.

- I2 - Login & Authorization

Features Microsoft 365–based authentication User login

Weekly Progress

Session timeout improvements — improved local storage management, integrated debug logging, and proper logout on timeout.

- I3 - Client, Member & Family Data

Features - Centralized person records (children, adults, limited profiles) - Duplicate prevention - Family and household structures - Multi-generation relationships Reciprocal relationship logic - Global search across people and families

Weekly Progress

Profile age checks and profile conversion logic merged.

Continued internal testing and UI refinements (contact cards, address book, critical-information toggle).

- I4 - Intake Management & Automated Notifications

Features - Structured intake workflows with mandatory fields - Intake status tracking and lifecycle - Supervisor review and approval processes - Ability to resolve intake without opening a case - Escalation from intake to case creation - Printable intake records - Automated notifications: - In-application alerts - Defined external channels (email/messaging)

Weekly Progress

Major iteration shipped — PRs #26 (intake-edit), #27 and #28 (bug-fix batches) merged to master.

Intake-to-case workflow refined based on the Apr 29 Ongoing Service walkthrough — design updates queued to reflect first assignment to reconciliation directors and director-driven supervisor/worker selection.

Eligibility banner messaging improved based on caregiver name and reason.

Safari date-picker fix (Apr 30 / May 1); tooltip additions on sticky header; submit-button error-state fix on update intake.

Sticky intake header refinements, timezone updates, and modal fixes.

Address book toggle tooltip fix; Critical Information toggle issue fix; phone-number mask prefill fix on edit.

- I5 - Case File Management & Signs of Safety

Features Case file creation and lifecycle management Assignment of caseworkers and supervisors Case reassignment with approval Signs of Safety–aligned workflows, including: - Placement - Structured assessments - Safety goals and planning - Ongoing review checkpoints - Visibility into historical and related cases Case notes for visits, services, and interactions Communication tracking across intake and case contexts - Document management: Person, Intake & Case

Weekly Progress

First wireframe walkthrough with the PCFS Ongoing Service Team completed Apr 29 (two parts).

Design updates queued from the walkthrough.

  - Director field on case record; admin screen for team configuration (Director → Supervisors → Workers).

  - Persons-in-case list to show address and in-home / out-of-home status plus links to any open related case files.

  - Conflict-of-interest access — move into safety/confidentiality using inclusion-based access.

  - Role-based dashboards aggregating tasks across cases and intakes, sorted by priority and due date.

  - CEPA-related case-change/completion handling to be clarified and documented.

Wireframes & Solution Design are in progress

Preliminary wireframes covering case record type, case notes, and placement require review with Ongoing Service Team. Marcus to reach out to Ross to schedule.

- I6 - Data Cleaning and Migration

Features Develop a data migration strategy from FAMCare into Waabanong Support PCFS as they perform data cleanup Execute trial data migrations in a sandbox environment Perform live data migration

Weekly Progress

No new updates this period — anonymization approach still being scoped.

- I7 - Financial Tracking & Exports for Sage

Features (Potential scope may include) Intake-level emergency supports Case-level budgets Spending caps and approvals Export files to import into Sage 300

Weekly Progress

Finance design session held Apr 28 with the PCFS finance team.

  - Defined dashboard with pending actions, supervisor approvals, and final finance approvals.

  - Credit-card transaction reconciliation flow including RBC export/import and receipt attachment.

  - Role-based task assignment using a new “finance assigner” role; global holiday calendar to drive business-hour timers and holiday coverage routing.

  - Audit and compliance — Wabana to store full transaction detail (receipts, approvals) for audit.

Recurring Tuesday finance working sessions confirmed; next session to review advanced wireframes for PO and credit-card reconciliation.

- I8 - My Dashboard & Reporting

Features (Potential scope may include) My Dashboard (simple, quick reference to key items) Tasks & alerts Reporting (if required and not covered in other iterations)

Weekly Progress

Future iteration per schedule (nothing this week).